## Sheet1
Property Scope of Work
Property Address: 1785 Santa Clara
Buyer Name:
Memphis, Tennessee 38116
Renovation Scope of Work
Home - General Interior
Repaint interior, two tone in semi gloss
New interior door handles as needed
Ensure all closets have doors/ poles and shelving
Install miniblinds throughout
Bathrooms x2 - Install new tile flooring,fiberglass tub, vanity, sink, and tile tub surround.
Ensure all plumbing is working correctly with no leaks
Install laminate wtaerproof flooring thoughout home
Ensure all electrical is fuctioning correctly all switches and knobs work, upgrade electrical service if needed
NEW hard surface countertop, sink, and faucet in kitchen. Refinish and paint base and wall cabinets in kitchen and install new hardware.
Home Exterior
Install new dimensional roof, 30 year shingle
Fix carport support pillar
Remove tree in front of home and clear debris off driveway. Powerwash driveway concrete.
Replace rotten wood around windows and trim as needed/ repair siding/paint exterior trim.
Paint exterior siding(not brick). Powerwash brick
Install new HVAC in home, 10 year warranty, with new insulated ducting.
Install new water tank
Install 1 Fire Extinguishers and 2 smoke detectors.
Deep Clean and other rent ready duties/ cut the grass /leaf pickup
All repairs and rehab work is warrantied for 30 days from the date of tenant move in
All permitting and MLGW connections with commensurate code inspection sincluded in price.
Aggregate Estimated Cost of Work | 65000