## Sheet1
Property Scope of Work
Property Address: 4079 Chippewa
Buyer Name:
Memphis, Tennessee 38118
Renovation Scope of Work
Home - General Interior
Repaint interior, two tone in semi gloss. Prep all walls and ceilings and smooth surfaces for finish. Leave wood paneling
New interior door handles as needed
Ensure all closets have doors/ poles and shelving
Install miniblinds throughout
Bathrooms x 1 - Install new tile flooring,fiberglass tub, vanity, sink, and tile tub surround.
Ensure all plumbing is working correctly with no leaks
Refinish hardwoods througout home OR finish installling waterproof LVP
Ensure all electrical is fuctioning correctly all switches and knobs work.
NEW hard surface countertop, sink, and faucet in kitchen. Install new base and wall cabinets in kitchen and install new hardware, and tile floor in 12x12 ceramic.
Home Exterior
Install new water tank
Landscape exterior, and remove all debris and detritus.
Paint exterior trim
Install new dimesnional roof, 30 year shingle
Install new HVAC system, 10 year parts warranty
Install 1 Fire Extinguishers and 2 smoke detectors and 2 CO2 detectors
Deep Clean and other rent ready duties/ cut the grass /leaf pickup
All repairs and rehab work is warrantied for 60 days from the date of tenant move in
All permitting and MLGW connections with commensurate code inspection sincluded in price.